## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	(Fill your Project Number here)
PROJECT NAME	(Fill your project name here)
PROJECT MENTOR (sponsor)	(Put your Project Mentor (sponsor) name here)
TEAM MEMBERS	Team Mamber Name 1
	Team Member Name 2
	Team Member Name 3
	Team Member Name 4
	Team Member Name 5

## Status
PROJECT NUMBER	SS05
PROJECT NAME	Fine grained Data visualization
PROJECT MENTOR (sponsor)	Dr. Kamal Karlapalem

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (August 8- August 14)
Fix meeting with client	Coordination	mohit	0.5	0.3	Done		0.2	66.6666666667
GIT Repository setup	Preparation	nikhil	1	0.1	Done		0.9	900
Client meeting	Coordination	yash	0.5	0.25	Done	Make sure scoping questions are included	0.25	100
Research existing technology	Preparation	yash,nikhil,mohit	18	14	Ongoing	OpenGL – nikhil, openCV – yash,mohit	4	28.5714285714
Project synopsis writeup	Documentation	mohit	1.5		Delayed	Idea about the project not clear
Identify role owners	Preparation	yash	0.5		Done	Multiple roles are OK - think about role & reponsibility distribution
Team Meeting	Coordination	nikhil	4	4	Done		0	0
Status tracker	Documentation	yash	0.5	0.4	Done		0.1	25
client’s initial demand	Development	nikhil	1	0.5	Done	need to plot 1000 random points in a graph
Week 2 (August 15 - August 21)
Fix meeting with client	Coordination	mohit	0.5	0.3	Done		Err:504	Err:504
Study openCV	Preparation	mohit	4	5	Done		Err:504	Err:504
Research possibilities	Preparation	yash	3	4	Done		Err:504	Err:504
Minutes of meeting	Documentation	nikhil	1	1	Done
Status tracker	Documentation	yash	1	0.5	Done
Team Meeting	Preparation	yash	2	3	Done
Project synopsis writeup	Documentation	mohit	2	2	Delayed	Clients suggested new ideas
Research point plotting options	Preparation	nikhil	3	4	Done
Week 3 (August 22 - sept 7)						Err:504	Err:504
Fix meeting with client	Coordination	mohit	0.5	0.2	Done		Err:504	Err:504
Delunay triangulation	Development	mohit,nikhil	5	3	Done		Err:504	Err:504
Heat map	Development	yash	5	3	Done		Err:504	Err:504
Project synopsis writeup	Documentation	mohit	1	0.5	Done
Status tracker	Documentation	yash	0.5	0.1	Done
SRS	Documentation	yash,nikhil,mohit	1.5	1.5	Done
Minutes of meeting	Documentation	nikhil	0.5	0.1	Done
Explore suggested ideas	Preparation	yash,nikhil,mohit	3	5	Done	Explore ideas suggested by us to client
Week 4(sept12 – sept21)						0.2	66.6666666667
Team Meeting	Preparation	nikhil	0.1	0.1	Done		-1	20
Improvising heatmap	Development	yash	2	2.5	Done		-1	25
Improvising delunay triangulation	Development	nikhil,mohit	3	2	Done
Week 5(sept22 – sept30)
Team Meeting	Preparation	mohit	0.2	0.5	Done		0.3	150
Extracting data from twitter and make heatmap	Development	yash	2	5	Done		2	66.6666666667
Detecting corner points	Development	mohit	1	1	Done
Animating denlunay triangulation	Development	nikhil	3	3	Done		2	66.6666666667
Making 3D model of given points	Development	mohit	1	2	Done
Implementing convex hull	Development	nikhil	0.3	0.3	Done
Making 3D heatmap of given 2D distribution	Development	yash	3	5	Done
Implementing new type of data visualization technique	Development	yash	2	4	Done
Week 6(oct1 – oct2)
make ppt	Preparation	yash,mohit	3	4	Done		0	0
prepare for presentation	Preparation	yash,mohit,nikhil	1	1.5	Done		-0.5	20
make website homepage	Development	mohit	2	3	Done
						-0.3	60
						-3	60
						0	0

						-1	25
						-0.5	33.3333333333
						-1	33.3333333333